Master Project Timeline — With Dependencies

Highlighted cells indicate tasks that are blocked by another member's output. Check the Dependencies column for details.

|  | Needs M1 |  | Needs M2 |  | Needs M3 |
| --- | --- | --- | --- | --- | --- |
|  | Needs M1+M2 |  | Needs M1+M3 |  | Needs M2+M3 |
|  | Independent |  | All members |  |  |

| Day | M1 | M2 | M3 | Dependencies |
| --- | --- | --- | --- | --- |
| PRE-WEEK — Setup & Foundations |  |  |  |  |
| Pre-1 | HAR download + verify | Python env + React | Docker + Gramine | — |
| Pre-2 | PCA decision + subject analysis | Opacus 6-class + eval script | Hello World in Gramine | — |
| Pre-3 | PCA fit + CSV plan | FastAPI + React panels 2+3 | PyTorch in Gramine + baselines | — |
| Pre-4 | 3 CSVs FROZEN + class weights | Dashboard panels 4+5+1 | Full stack in Gramine + Minikube + K8s YAMLs | — |
| Pre-5 | Deployment scenario draft | TLS certs + E2E dashboard test | Crypto layer + attestation demo | — |
| WEEK 1 — FL Core + DP Integration |  |  |  |  |
| W1-1 | PyTorch model + data loader | DP trainer | Expand manifest + enclave benchmarks | — |
| W1-2 | Flower server + client skeleton | Dashboard Panel 6 + graph infra | Dockerfiles | — |
| W1-3 | Connect FL locally (4 terminals) | DP into FL client | docker-compose.yml | M2: needs M1 ¦ M3: needs M1+M2 |
| W1-4 | docker-compose 20 rounds | All 4ε experiments + Graphs 1+2 | K8s full deploy + network policy | M1: needs M3 ¦ M2: needs M1+M3 ¦ M3: needs M1+M2 |
| W1-5 | Deployment scenario + report intro | Graphs 3+4+5 + dashboard live | STRIDE Spoofing category | M1: needs M2+M3 ¦ M2: needs M1 ¦ M3: needs M1 |
| WEEK 2 — Gramine Integration + Reports |  |  |  |  |
| W2-1 | Crypto into FL communication | Report: DP methodology | FL server inside Gramine | M1: needs M3 |
| W2-2 | Report: dataset section | Dashboard ε visual + graph polish | All 3 clients inside Gramine | — |
| W2-3 | Report: FL methodology | Run cross-validation | SGX sealed storage | M1: needs M2+M3 ¦ M2: needs M1 |
| W2-4 | Handoff prep FINAL | Attestation Panel 1 + arch report | Attestation into FL server | M1: needs M2+M3 ¦ M2: needs M3 ¦ M3: needs M2 |
| W2-5 | Handoff docs verified | Demo recording + report outline | Full K8s SGX pod cold start | M3: needs M1+M2 |
| WEEK 3 — Integration, Attacks & Security |  |  |  |  |
| W3-1 | Final handoff prep | ε analysis notes | STRIDE Tampering + Info Disclosure | — |
| W3-2 | Architecture + scenario final | Eval methodology report | Complete FL+DP in Gramine 10 rounds | M1: needs M2+M3 |
| W3-3 | HANDOFF + related work | Attack 1: Model Inversion | Full FL+DP+K8s SGX after handoff | M1: needs M2+M3 ¦ M3: needs M1+M2 |
| W3-4 | FL methodology + limitations | Attack 2: Membership Inference | Final TEE overhead benchmarks | M2: needs M1+M3 ¦ M3: needs M2 |
| W3-5 | Report compilation draft | Graph 6 real numbers + results report | STRIDE complete + all security reports | M1: needs M2+M3 ¦ M2: needs M1+M3 ¦ M3: needs M1+M2 |
| WEEK 4 — Final Integration & Slides |  |  |  |  |
| W4-1 | Report compilation FINAL | Attack 3: Gradient Poisoning | TEE + Security report sections | — |
| W4-2 | Slides 1–6 | Slides 7–12 | Slides 13–17 | — |
| W4-3 ¦ ALL: Full integration cold start test → Report proofread |  |  |  |  |
| W4-4 ¦ ALL: Report final + demo machine setup |  |  |  |  |
| W4-5 ¦ ALL: Full Rehearsal 1 + Q&A practice |  |  |  |  |
| WEEK 5 — Submission & Presentation |  |  |  |  |
| W5-1 ¦ ALL: Final checks per member |  |  |  |  |
| W5-2 ¦ ALL: Full Rehearsal 2 + SUBMIT ✓ |  |  |  |  |
| W5-3 ¦ ALL: Final cold start test + rest |  |  |  |  |
| W5-4 ¦ ALL: PRESENT ✓ |  |  |  |  |